## Phase Overview
Phase | Goal | Steps | Done | % complete
1 Foundation | Repo, environments, auth, profiles, RLS, design system, seed catalogue | 8 | 0 | 0%
2 Library & Reviews | Search, book pages, shelves, reviews, reactions, reports | 9 | 0 | 0%
3 Profiles, Avatars, Journal | Profile + privacy, layered avatars, focus timer, journal and stats | 9 | 0 | 0%
4 Crossword | Validated daily puzzle, accessible grid, server-side completion, streaks | 7 | 0 | 0%
5 Café | Illustrated room, seat claims, realtime presence, audio, focus sessions | 8 | 0 | 0%
6 QA & Release | Security/concurrency tests, e2e, accessibility, deploy, backups | 6 | 0 | 0%
Total |  | 47 | 0 | 0%
Stack: Next.js 16 + TypeScript (App Router), Supabase (Postgres, Auth, Realtime, Storage, Edge Functions). Update Status in 'Execution Plan'; this sheet recalculates.

## Execution Plan
Phase | Step | Task | Done when | Depends on | Size | Status
1 Foundation | 1.1 | Create repo; scaffold Next.js 16 + TypeScript (App Router) + Tailwind; ESLint, Prettier, Git | App runs locally; lint and typecheck pass |  | S | Not started
1 Foundation | 1.2 | Create Supabase dev and prod projects; install Supabase CLI; set up local stack and .env files | supabase start works; secrets documented; no service-role key in client code | 1.1 | S | Not started
1 Foundation | 1.3 | Add @supabase/ssr client helpers (browser, server) and request-interception layer (proxy) for session refresh | Session persists across reloads; protected route redirects with safe return path | 1.1, 1.2 | M | Not started
1 Foundation | 1.4 | Migration: profiles table (case-insensitive unique username), trigger to create profile on signup, RLS policies | New signup creates one profile; user can edit only own row | 1.2 | M | Not started
1 Foundation | 1.5 | Auth pages: /signup, /login, /forgot-password, logout; unique username validation | All four flows work end to end with accessible errors | 1.3, 1.4 | M | Not started
1 Foundation | 1.6 | Design tokens (palette, fonts), base components, desktop sidebar and mobile bottom nav shell | Shell renders on desktop and mobile; active route shown; reduced-motion respected | 1.1 | M | Not started
1 Foundation | 1.7 | Migration: books, genres, book_genres; seed curated catalogue; public-read RLS | Seed loads cleanly; guests can read books, nobody can write from client | 1.2 | M | Not started
1 Foundation | 1.8 | RLS test harness (two test users + guest) and CI run | Tests fail when a policy is removed | 1.4, 1.7 | M | Not started
2 Library & Reviews | 2.1 | Library page: search by title/author, genre filter, sort, pagination; indexes | Search is fast; pagination works; empty and error states shown | 1.7 | M | Not started
2 Library & Reviews | 2.2 | Book detail page (server-rendered): metadata, tags, related books, cover optimisation | Deep link works after refresh; metadata/OG tags set | 2.1 | M | Not started
2 Library & Reviews | 2.3 | Migration: shelves, shelf_books with uniqueness; RLS; default statuses | User cannot read another user's private shelves (test passes) | 1.4, 1.7 | M | Not started
2 Library & Reviews | 2.4 | Shelves UI: add/remove book, move between statuses, custom lists, currently-reading card | Changes persist across devices; no duplicate entries | 2.3 | M | Not started
2 Library & Reviews | 2.5 | Migration: reviews (rating, headline, body, quote, tags, spoiler, status); RLS; length constraints | Users can edit/delete only own reviews (test passes); guests blocked from writing | 1.4, 1.7 | M | Not started
2 Library & Reviews | 2.6 | Review CRUD + draft/publish; 'The Shelf' mode; safe rendering of user content | Create/edit/delete works; HTML is escaped | 2.5 | L | Not started
2 Library & Reviews | 2.7 | 'The Margins' mode and spoiler warning gate | Spoiler content hidden until user reveals | 2.6 | S | Not started
2 Library & Reviews | 2.8 | review_reactions (unique per user/review) and aggregate rating/count from published ratings | Duplicate reaction rejected; aggregates match real data | 2.6 | M | Not started
2 Library & Reviews | 2.9 | review_reports table and report UI; restricted-access RLS | Report saved; only moderators can read reports | 2.6 | S | Not started
3 Profiles, Avatars, Journal | 3.1 | Profile edit page: bio, genres, reading goal, privacy settings | Updates persist; email never exposed publicly | 1.5 | M | Not started
3 Profiles, Avatars, Journal | 3.2 | Public profile /profile/[username] respecting privacy for shelves, reviews, stats | Private data never appears in public queries (test passes) | 2.4, 2.6, 3.1 | M | Not started
3 Profiles, Avatars, Journal | 3.3 | Migration: avatar_items, user_avatar_items; store avatar config as item IDs; seed free wardrobe | Catalogue seeded; config schema validated | 1.4 | M | Not started
3 Profiles, Avatars, Journal | 3.4 | Layered avatar renderer (consistent anchors, layer order) and editor UI | Avatar renders identically in editor, profile and nav | 3.3 | L | Not started
3 Profiles, Avatars, Journal | 3.5 | Server-side equip validation (ownership and compatibility) | Equipping an unowned item is rejected (test passes) | 3.3 | S | Not started
3 Profiles, Avatars, Journal | 3.6 | Migration: reading_sessions (type, start/end, duration, book, note, source); RLS | Sessions are private to owner | 1.4 | M | Not started
3 Profiles, Avatars, Journal | 3.7 | Focus timer UI: 25/5, 50/10, custom; pause/resume/cancel/finish; interruption handling | Closing the tab does not log the full planned time | 3.6 | M | Not started
3 Profiles, Avatars, Journal | 3.8 | Session completion function: duplicate and implausible-duration checks; manual vs timer-verified flag | Repeated completion creates one record | 3.6, 3.7 | M | Not started
3 Profiles, Avatars, Journal | 3.9 | /journal history, weekly/monthly totals; /settings incl. safe account deletion | Totals computed from authorised records; deletion behaviour documented | 3.8 | M | Not started
4 Crossword | 4.1 | Migration: crossword_puzzles, crossword_completions (unique user/puzzle); seed one validated puzzle | Puzzle row passes grid/clue validation | 1.7 | M | Not started
4 Crossword | 4.2 | Fetch today's puzzle without sending the solution to the client | Network response contains no answers | 4.1 | S | Not started
4 Crossword | 4.3 | Grid UI: keyboard and mobile input, current cell/direction, clue navigation | Playable on desktop and mobile | 4.2 | L | Not started
4 Crossword | 4.4 | Accessibility: cell announcements, focus indicators, error feedback | Keyboard-only and screen-reader pass | 4.3 | M | Not started
4 Crossword | 4.5 | Server-side completion validation (Edge Function or RPC) with one completion per user/puzzle | Fake solutions rejected; repeated requests award once (tests pass) | 4.1 | M | Not started
4 Crossword | 4.6 | Streak calculation with configured timezone/day boundary; define replay/catch-up rules | Boundary cases tested around midnight | 4.5 | M | Not started
4 Crossword | 4.7 | Completion screen revealing the book; completion history on dashboard | Screen shows after valid completion only | 4.5, 4.6 | S | Not started
5 Café | 5.1 | Migration: cafe_rooms, cafe_seats, cafe_sessions; seed rooms and seats | Rooms/seats defined; occupancy not stored as sole truth | 1.4 | S | Not started
5 Café | 5.2 | Static illustrated 2D room UI with entrance transition (skippable) | Four areas render; works with reduced motion | 1.6 | L | Not started
5 Café | 5.3 | Seat-claim function (atomic) with release on leave | Two simultaneous claims: exactly one wins (test passes) | 5.1 | M | Not started
5 Café | 5.4 | Realtime Presence channel with authorised join and payload validation; stale presence cleanup | Disconnected users drop out; no fake users shown | 5.2, 5.3 | L | Not started
5 Café | 5.5 | Avatar activity states (read, study, journal, break) shown in room | State changes broadcast to others | 3.4, 5.4 | M | Not started
5 Café | 5.6 | Connect focus timer to café sessions and journal | Completed café session appears in journal | 3.8, 5.4 | M | Not started
5 Café | 5.7 | Ambient audio: user-initiated, volume/mute, never autoplay | No audio until user acts; mute persists in session | 5.2 | S | Not started
5 Café | 5.8 | Mobile simplified café layout; optional noticeboard | Usable at narrow widths | 5.2 | M | Not started
6 QA & Release | 6.1 | Run full RLS test list with separate accounts and guest | All 12 PRD required tests documented/automated | all | M | Not started
6 QA & Release | 6.2 | Concurrency and duplicate-request tests (seat claims, completions, reactions) | No duplicates under parallel requests | 5.3, 4.5, 2.8 | M | Not started
6 QA & Release | 6.3 | Playwright e2e on key flows; mobile and keyboard checks | Core routes pass on desktop and mobile | all | L | Not started
6 QA & Release | 6.4 | Security review: secrets, input validation, rate limits on abuse-prone endpoints | No privileged keys in client; limits in place | all | M | Not started
6 QA & Release | 6.5 | Deploy to production; separate prod credentials; domain | Production works with prod Supabase project | 6.1-6.4 | M | Not started
6 QA & Release | 6.6 | Backups, restore test, monitoring, setup docs and env var list | Restore verified; README complete | 6.5 | S | Not started
Size is a rough relative effort guide (S, M, L), not a time estimate. Phase order follows PRD section 14; steps are split so each can be built and tested on its own.